## Slide 1: OVERVIEW OF LOCAL GOVERNMENT CONSTRUCTION OPTIONS
by
Jeff Qualkinbush, Esquire Barnes & Thornburg LLP 11 South Meridian Street Indianapolis, Indiana 46204 (317) 231-7753
jqualkinbush@btlaw.com
Notes: <number>

## Slide 2: Available Construction Methods
Design-Bid-Build (Indiana Code 36-1-12)
Guaranteed Savings (Indiana Code 36-1-12.5)
Design-Build (Indiana Code 5-30)
Construction Manager as Constructor (Indiana Code 5-32)
Notes: <number>

## Slide 3: Design-Bid-Build Method
Highlights of the process
  The governmental entity must hire an architect or engineer to prepare detailed plans and specifications
  The governmental entity may not have plans and specifications that “unduly limit competition” which may make it difficult to pre-qualify bidders
  The governmental entity may also hire a construction manager, an owner’s representative/clerk of the works or the architect/engineer to supervise the construction
Notes: <number>

## Slide 4: Design-Bid-Build Method (cont’d.)
Highlights of the process (cont’d.)
  The governmental entity publicly bids the construction project and awards the construction contract to the lowest responsive and responsible bidder
  Minimum 15-day response period required, but may be longer
  Payment and performance bonds and retainage are required
  The timeline from the beginning of design to award of the construction contract for a $1,000,000-10,000,000 project is normally 4-7 months
Notes: <number>

## Slide 5: Design-Bid-Build Method (cont’d.)
Primary Positives
  This method has been used most often by local and state governmental entities and has a long history
  The public bidding ensures the governmental entity is getting the lowest bid by the bidding market on the day bids are received
  The architect, engineer, construction manager or owner’s representative/clerk of the works provides the governmental entity an objective third party to review the work being performed by the contractor
  The governmental entity gets the benefit of any unused contingency
Notes: <number>

## Slide 6: Design-Bid-Build Method (cont’d.)
Primary Negatives
  The governmental entity may not be able to avoid using a problem contractor if the contractor submits the lowest responsive bid
  The governmental entity will incur the design fees earlier
  Change orders are common
  If there is a defect in the project, everyone is blaming everyone else for the defect
  No measurable way to incentivize good performance or punish bad performance
Notes: <number>

## Slide 7: Guaranteed Savings Method
Highlights of the process
  The governmental entity may, but is not required to, hire an architect or engineer
  The governmental entity prepares and issues a Request for Proposals pursuant to a public notice
  Minimum 37-day response period required, but may be longer
  The governmental entity, either on its own or with the assistance of an architect/engineer, awards the guaranteed savings contract to the qualified provider on the basis determined to be most beneficial to the governmental entity
Notes: <number>

## Slide 8: Guaranteed Savings Method (cont’d.)
Highlights of the process (cont’d.)
  The qualified provider must have (a) an Indiana registered engineer as a part of the team, (b) be certified by the State of Indiana to perform the types of work involved in the project, and (c) perform at least 20% of the work
  The qualified provider may subcontract portions of the work
  Payment and performance bonds in the amount of the guaranteed savings contract are required
  No retainage is required
Notes: <number>

## Slide 9: Guaranteed Savings Method (cont’d.)
Highlights of the process (cont’d.)
  The savings (guaranteed actual or stipulated) created by the conservation measures must be equal to or greater than the cost of the measures over a term not to exceed the lesser of the useful life of the conservation measures or 20 years
  The project may include some non-conservation measures
  The contract can be either a guaranteed maximum price contract or a cost plus percentage contract
  The contract may identify a contingency and how that is shared by the parties
Notes: <number>

## Slide 10: Guaranteed Savings Method (cont’d.)
Highlights of the process (cont’d.)
  Change orders permitted in only limited situations or if there is a change in scope
  The governmental entity may hire an owner’s representative/clerk of the works to monitor performance of the qualified provider
  The timeline from the publication of the Request for Proposals to execution of the guaranteed savings contract for a $1,000,000-10,000,000 project is normally 3-5 months
  Annual savings reports must be filed with the State of Indiana
Notes: <number>

## Slide 11: Guaranteed Savings Method (cont’d.)
Primary Positives
  The selection process is not limited by statute and allows the governmental entity to select the qualified provider on whatever basis it determines to be desirable to the governmental entity
  Limitations may be imposed on who may be an acceptable respondent
  The upfront (but not overall) professional costs incurred by the governmental entity are significantly less
  Usually few or no change orders
  The timeline for selection of the qualified provider is shorter
Notes: <number>

## Slide 12: Guaranteed Savings Method (cont’d.)
Primary Positives (cont’d.)
  Incentives and penalties can be included in the contract
  If there is a defect in the project, then the qualified provider is solely responsible for correcting the problem at its cost
  In general, governmental entities have found this process to require less involvement in the project by the governmental entity
Notes: <number>

## Slide 13: Guaranteed Savings Method (cont’d.)
Primary Negatives
  The timeline for the process and the preparation to be done by the respondents may reduce the pool of respondents depending on the size of the project and the time allowed for responses
  The governmental entity may not be able to provide satisfactory objective information regarding why one qualified provider was selected over the other respondents
  The governmental entity may lose all or a portion the benefit of a project coming in under budget
  Unclear as to the actual amount of the energy/operational savings obtained
Notes: <number>

## Slide 14: Design-Build Method
Highlights of the process
  The governmental entity must hire an architect or engineer to prepare and issue a Combined Request for Qualifications/Request for Proposals (for projects costing $5,000,000 or less) or a Request for Qualifications followed by a Request for Proposals (for projects costing more than $5,000,000) in accordance with a public notice
  Minimum 37-day response period (for projects costing $5,000,000 or less) or 15-day response period required (for projects costing more than $5,000,000), but can be longer
Notes: <number>

## Slide 15: Design-Build Method (cont’d.)
Highlights of the process (cont’d.)
  The governmental entity creates a committee (containing a licensed architect and engineer along with others) that scores all aspects of the responses submitted except the sealed price proposals
  The governmental entity awards the design-build contract to the respondent that provides the best value based on the respondent’s score relative to its price
  The design-builder selected is responsible for both the design and the construction of the project
  The contract can be either a guaranteed maximum price contract or a cost plus percentage contract
  The contract may identify a contingency and how that is shared by the parties
Notes: <number>

## Slide 16: Design-Build Method (cont’d.)
Highlights of the process (cont’d.)
  Change orders permitted in only limited situations or if there is a change in scope
  Payment and performance bonds are required in the amount of the contract minus design service fees
  No retainage required
  The governmental entity may hire an owner’s representative/clerk of the works to monitor performance of the design-builder
Notes: <number>

## Slide 17: Design-Build Method (cont’d.)
Highlights of the process (cont’d.)
  The timeline from the creation of the Combined Request for Qualifications/Request for Proposals to approval of the design-build contract for a $1,000,000-5,000,000 project is normally 3-5 months
  The timeline from the creation of the Request for Qualifications to approval of the design-build contract for a $5,000,000-10,000,000 project is normally 5-7 months
Notes: <number>

## Slide 18: Design-Build Method (cont’d.)
Primary Positives
  The scoring process, which involves an engineer and an architect, provides for transparency and allows for a best value award instead of a low bid award
  Limitations may be imposed on who may be an acceptable respondent
  The upfront (but not overall) professional costs incurred by the governmental entity are significantly less
  Usually few or no change orders
Notes: <number>

## Slide 19: Design-Build Method (cont’d.)
Primary Positives (cont’d.)
  Incentives and penalties can be included in the contract
  If there is a defect in the project (with certain exceptions for latent defects such as soil defects), then the design-builder is solely responsible for correcting the problem at its cost
Notes: <number>

## Slide 20: Design-Build Method (cont’d.)
Primary Negatives
  The timeline for the process and the preparation to be done by the respondents may reduce the pool of respondents depending on the size of the project
  Some, or much, of the control of the governmental entity over the design of the project may be lost
  The governmental entity may lose all or a portion the benefit of a project coming in under budget
  Unclear whether there are really cost savings
  The timeline for the selection of the design-builder is very similar to the Design-Bid-Build Method
Notes: <number>

## Slide 21: Construction Manager as Constructor Method
Highlights of the process
  The governmental entity must hire an architect or engineer to prepare detailed plans and specifications like it would for the Design-Bid- Build Method
  The governmental entity hires the Construction Manager using a Request for Proposals process pursuant to a public notice
  Minimum 15-day response period required, but may be longer
  The Construction Manager is selected by an evaluation committee subject to governing body approval
Notes: <number>

## Slide 22: Construction Manager as Constructor Method (cont’d.)
Highlights of the process (cont’d.)
  Unlike the design-build method, there is no specific requirement regarding the composition of the evaluation committee
  After the Construction Manager is selected, the public bidding of the construction contracts occurs by the Construction Manager
  The construction contracts are awarded by the Construction Manager to the lowest responsive and responsible bidder for each trade
  The Construction Manager, not the governmental entity, enters into the contracts with the contractors
Notes: <number>

## Slide 23: Construction Manager as Constructor Method (cont’d.)
Highlights of the process (cont’d.)
  The potential bidders may be pre-qualified if the pre-qualifications are in writing and approved and published by the governmental entity
  A guaranteed maximum price may be used, but not required
  Payment and performance bonds are required in the amount of the Construction Manager’s contract
  No retainage required
  The governmental entity may also hire an owner’s representative/clerk of the works or an architect/engineer to supervise the construction on behalf of the owner
Notes: <number>

## Slide 24: Construction Manager as Constructor Method (cont’d.)
Highlights of the process (cont’d.)
  The Construction Manager may perform construction work on the project if it is approved by the governmental entity, the work equals less than 20% of the total value of the project and the Construction Manager can provide evidence to the governmental entity that it is charging less for that work than the lowest responsive and responsible bidder for such work
  The timeline from the beginning of design to award of the construction contracts for a $1,000,000-10,000,000 project is normally 4-7 months
Notes: <number>

## Slide 25: Construction Manager as Constructor Method (cont’d.)
Primary Positives
  The governmental entity maintains control of the design of the project
  The public bidding of the construction contracts ensures the governmental entity is getting the lowest bid by the bidding market on the day bids are received; however, this is only economical beneficial to the governmental entity in a cost-plus contract
  The governmental entity may pre-qualify and limit the bidders for the construction work
Notes: <number>

## Slide 26: Construction Manager as Constructor Method (cont’d.)
Primary Positives (cont’d.)
  The architect, engineer or owner’s representative/clerk of the works provides the governmental entity an objective third party to review the work being performed by the contractor
  The governmental entity may get the benefit of any unused contingency
  Penalties and incentives may be included in the contract with the Construction Manager and the contractors
Notes: <number>

## Slide 27: Construction Manager as Constructor Method (cont’d.)
Primary Negatives
  The governmental entity will incur the design fees earlier
  The governmental entity may experience change orders related to design issues
  If there is a defect in the project, everyone is blaming everyone for the defect
  The governmental entity may lose all or a portion of the benefit of a project coming in under budget if the contract is a guaranteed maximum price contract
  The timeline for the project is very similar to the Design-Bid-Build Method
Notes: <number>