## TCSC Greenhouse Project Budget
Tipton Community Schools Corporaton (TCSC) Greenhouse Project Budget
Goal: To Provide Stakeholders with a Realistic Cost Estimate for the Project
| Authors | Matt Smith/Jim Ankrum
| Budget Items | Vendor/Subcontractor | Budget - Base Scope | Budget - Greenhouse and Foundation Wall Only | Budget - Foundation Wall and Storage Facility | Notes
| Architecture/Engineering Fees | Alpha 5 Architects | 7700 | 7700 | 7700 | Estimate obtained from Andy Fish - Alpha 5 Architects
| Site Design | 40th Parallel Surveying | 3000 | 3000 | 3000 | Estimate obtained from Wyatt Johnson
| Permit Fees | TBD | 1500 | 1500 | 1500
| Construction Management and Storage Building Construction | Keith Smith | 7000 | 21500 | 68800 | Estiamte obtained from Keith Smith
| Excavation/Concrete | Tragesser Concrete | 14692 | 23788 | 33994 | Estimate obtained from Brent Tragesser.
| Plumbing | BRS Mechanical | 16400 | 16400 | 16800 | Estimate obtained from BRS
| HVAC | Nick Stewart Heating and Cooling | 12000 | 12000 | 20000 | Verbal estimate obtained from Nick Stewart
| Electrical | Omni Electric | 32100 | 32100 | 38600 | Estimate obtained from Omni Electric
| Building Component Upgrades (replacement parts and replacement translucent panels) | Harnois Buildings | 10000 | 10000 | 10000 | No estimate obtained. Assumed cost of building constituents.
2017-06-13 | Asphalt Repairs | Baumgartner Asphalt | 5000 | 5000 | 7000 | Formal proposal not obtained.
| Allowance for furnishings, irrigation and fertilizer system | None | 6000 | 6000 | 6000 | This is just an estimate.
| Allowance for floodplain mitigation work. | None | 8000 | 8000 | 10000 | Estimate - school property is in floodplain, so fill for building will need to be offset by removal of fill - likely adjacent to wetland area north of bus barn.
| Contingency | None | 25000 | 29000 | 40000
2017-06-13
2017-06-13 | Total Capital Improvement Budget |  | 148392 | 175988 | 263394
| Total Construction Amount |  | 118192 | 145788 | 231194 | Target is to be under 150,000 due to public bidding requirements.
2017-06-08 | TCSC Operation and Maintenance (O&M) Yearly Budget
Other Notable Information
2017-06-07
2017-06-07
2017-06-05
2017-06-05
2017-06-07
2017-06-05
2017-06-05