## HP2 Summary
Tipton COMMUNITY SCHOOLS
PROJECT BUDGET SHEET
| Date: | UPDATED 9/19/23 | 2023-11-21
2023/2024 High School Renovation Project |  |  |  | Comment
Bond Sale Proceeds |  |  | 5815000 | To be confirmed upon sale of the Bond
Cost of Issuance |  |  | 360000 | Anticipated
Total Soft Costs |  |  | 714061.83
Total Available for Project |  |  | 4740938.17
| Proposed GMP |  | 4739684
| Difference |  | -1254.17
Soft Costs
Schmidt Base Design Fees |  | 7% | 322000
Schmidt Reimbursable Expenses Allowance -10% |  | 10% | 20000 | estimated- reduced from $32,200
Owner's FFE Allowance (Furniture, Loose Equipment) |  |  | 253328
FFE Design Fee- 5% |  |  | 12666.4 | Fee reduced to 5%
Point Cloud Surveys |  |  | 19910 | actual $79,640/4 Projects
Permitting, Variances, State Release (allowance) |  |  | 157.43 | actual
Asbestos Testing/Abatement Allowance |  |  | 0 | In GMP
Fire Alarm Work - Owner Allowance |  |  | 15000
Relocate PA System- Owner Allowance |  |  | 10000
Electrical Lighting- Owner Allowance |  |  | 10000
Relocate Door Control Panel- Owner Allowance |  |  | 10000
Hall of Fame Technology Hard/Software Allowance |  |  | 10000
Sprinkler Work |  |  | 31000
Sanitary Piping Contingency- Allowance |  |  | 0
Owner Contingency |  |  | 0 | was $100,000, took PA, FA, Door controller, HOF out of this
Total Soft Costs |  |  | 714061.83