## Sheet1
Tipton HS Renovations Package 2 Post Bid VE Options
As of November 21, 2023
| 1. Eliminate the replacement of existing wood doors and hardware at openings at 1st Floor Openings: 173, 175, 177, 179, 181, 183, 185, 188, 186, 184, 182, 180 (12) and at 2nd Floor Openings: 275, 276, 277, 278, 279, 280, 281, 282, 283, 284, 285, 286, 287 (13) for total of 25 openings. | 2. Eliminate the new HM frames/door and hardware for openings under the Stage: 126.7, 126.8, 126.9, 126. 10, 126.11, 126.12, 126.13 and 126.14. (8) | 3. In lieu of replacing existing Vestibule 100 alum entry with new Elevation SF3, relocate existing alum entry framing/doors/hardware to new location. | 4. Eliminate ALL painting in Gym 126 and Stage 126E including exposed steel structure, walls, basketball goal support framing and gym side hollow metal frames/doors. No Gym side painting. | 5. Eliminate ALL painting of frames/ walls, flooring/base and visual display boards (VDB’s) in the following 1st floor rooms: 175, 177, 179, 181, 183, 185, 188, 186, 184, 182, 180 and 2nd floor rooms: 275, 276, 277, 230, 279, 280, 281, 282, 283, 284, 285, 286, 287 | 6. Eliminate work associated with flooring pool deck flooring replacement in Natatorium 120 | 7. Deduct to Base Bid to only replace the (2) main court basketball ball backboards, nets, padding and rims. (No work on the four side backboards) | 8. Eliminate the CWT in restrooms 121H, 123B, 121J, 123A and Concession 121 N and paint these walls | 9. Eliminate the RSF and RSFB in restrooms 121H, 123B, 121J and 123A and add VCT-1 flooring and VWB-1 in these rooms. | 10. Eliminate the replacment of openings 127, 128A, 129, 130B, 130A, 163, 167.3 and 167.2. | 11. Delete the frame/DR/HW replacment for openings in the Natatorium at B114 and B115. | 12. Eliminate the replacement of Electrical Panel "1L4" | 13. Elimanate Replacment of Electrical Panel "T" | 14. Eliminate replacement of the Middle School Exit Lights and Upper Gym seating lights
Total Deducts as of 11/21/23 | -44057 | -19628 | -12650 | 0 | -136770 | -103601 | -14773 | -32315 | 288 | -27938 | -11607 | -28460 | -14991 | -13335 | -459837
[10 empty] | Complete Nov. 17, 2023 | Complete Nov. 17, 2023
0